## Sheet1
Rank 1, 2, or 3 | PROJECT/TASK UPDATED: 7-23-20 | RATED 1-3 & LONG-RANGE | RESPONSIBLE DEPT. | COMMENTS/UPDATES | STATUS | Staff Notes 7/21/20
High Priority Projects
1 | Affordable Housing (Market Rate/Working Class) | 2 | AHTFB/EDC | Housing needs study funded by CPA is underway, for completion summer 2020 | WIP
1 | Ambulance Service Study | LONG-RANGE | Fire Dept. | Chief Burger is working with SBVAS/Fairview/REPC to evaluate next steps/study. |  | CR updated
1 | Cook's Garage Property | 1 | TM/Treasurer-Coll. | Awaiting issuance of Ph.II report. Discuss next steps with HIC / community in fall-winter? | WIP
1 | COVID-19 State of Emergency | 1 | ALL |  |  | Can this be made "Long Range" or deleted? I don't see any owner paying more $ right now, if ever. - CR
1 | Hous. Com. Center (updates/conf. room/grants) | 2 | TM/DPW | Green Com. Competitive grant application submitted. Likely awards in August 2020 | WIP
1 | Housatonic Fiber | 1 | Planning Dept | Study funded at 2020 ATM, to begin in fall 2020 | WIP | CR Updated
1 | HR Director (Shared Position?/Shared w/BHRSD?) | 2 | TM | TM will reach out to BHRSD to gauge interest in a shared position |  | CR updated
1 | Infrastructure (Bridges/Roads/Sidewalks) | 1 | TM/DPW | Merged line: Division and Cottage Bridges, LM Road, etc. |  | SV Updated
1 | Parking Concerns- RFP | 2 | TM/Planning Dept./EDC | Updated map posted, shared with Chamber. New map updated showing loss of Foster's | WIP | I don't know what this means exactly, but the Cultural District is for this purpose. - CR
1 | Personnel Policy/Manual | 1 | TM/Treasurer-Coll./Fin. Dir. | In draft format at this time. Funded through grant. Expected completion fall 2020. | WIP | CR updated
1 | Reid Cleaners Property | 1 | TM/Planning Dept. | EPA to do soil removal this year. Grant $ received, this phase to begin mid '21 | WIP | SV Updated
1 | Systemic Racism Proclamation | 1 | TM | Merged Line to include Proclamation/Trust Policy/Committee formations from Proclamation |  | CR updated
1 | Trip Hazards Main Street | 1 | DPW | DPW working to address hazards over time. Expected 2021-2023 as budget allows | WIP
1 | Water Systems Study | 1 | TM/DPW | Engineering funds are availble for next phase of study | WIP
Moderate Priority Projects
2 | 5G Technology | LONG-RANGE | Planning/SPM | Report provided to the PB. SPM will work on presentation to SB at a later date. | WIP | special town meeting?
2 | Business Improvement District | 2 | EDC/Planning Dept. | Economic Development Committee task? |  | We applied for MVP action grant to include outreach - CR
2 | Committee Charters- Mtg. of Chairs | 2 | SPM | SPM and @GBLABS are working on this and will report back at a later date. | WIP | SV Updated
2 | Conservation Fund for Land Purchases | 2 | Con-Com | FY22 discussion. CPA application denied for FY21. | WIP | CR updated
2 | Court House Improvements | 1 | TM/DPW | Bathroom work on the court has been completed all other work is on hold because of COVID | WIP | CR updated
2 | Downtown (Pride/energy/marketing/entertainment) | 2 | Planning/Cultural District | Cultural District promotions ongoing. Applied for "shared street" grant for RR Street dining | WIP
2 | Econ. Dev/Small Biz Assistance | LONG-RANGE | Planning Dept./EDC | Town with BRPC et al. should hear re: CDBG-CV biz. assistance grants in July-Aug. | WIP | MP updated
2 | Elevator Repairs | 1 | DPW | Engineering work will start this summer for a repair this winter. Funding approved in 2020/ATM | WIP
2 | EV Charging Station | 2 | DPW | DPW incorporating into plans for Taconic lot and future plans for Town Hall lot | WIP | MP updated
2 | Fire Department Study | 2 | TM/Fire Dept. | Chief Burger is implementing some recommendations now.
2 | Fire Station Easement- Telephone Pole/utility | 3 | TM/DPW | Working with DPW Superintendent, N-Grid, and Property Owner |  | CR updated
2 | Grove Street Property | 1 | TM/Treasurer-Col/DPW | SB Vote to auction. Property sale on hold pending further discussion. | WIP
2 | Hosting Community Discussions w/BRIDGE | 2 | TM | Proposal from BRIDGE. Looking at FY21 depending on available funding |  | MP Updated
2 | Hous. School- Updates | 1 | TM/Planning/EDC | Staff updating cost estimates. HIC is also reviewing this issue. | WIP | MP updated
2 | Inclusiveness/Diversity (Town Hall/Town-wide) | 1.2.3 | TM | Translation tablets @ all town builidngs. Diversity training postpoded during COVID. | WIP | Mark, maybe by 8/3 meeting we will have a draft lease / rfp to show them? - CR
2 | Licensing Board | 1 | TM/SPM | 1-day wine/malt, vending, entertainment, auto sales, annual renewals |  | MP updated
2 | Marijuana Lic. Limits- Marijuana Revenue | 1 | SB/TM | Zoning article proposed for STM in September 2020. | WIP
2 | Marketing to young families | LONG-RANGE | EDC/Planning Dept. | EDC Task. |  | CR updated
2 | Master Plan Review w/PB | 2 | Planning Dept. | For continued discussion at SB/PB joint meetings (see #7 below) |  | CR updated
2 | Mission Statement for SB and Town | 1 |  |  |  | Also should update permit applic fees due to higher advert. costs - CR
2 | Neighborhood Meetings/Mtgs in Housatonic | 1 | TM | Cottage, Grove, and Housatonic meetings held. Portable sound system needed. On-hold during Covid | WIP | SV Updated
2 | Open Mtg/Public Records training for boards | 1 | TM/Town Clerk | State trianing scheduled for spring 2020 was cancelled due to COVID
2 | Policy for Removing Committee Members | 1
2 | Rest of River Status | 1 | Planning Dept./TM | Settled Feb. 2020. EPA revised permit comment period through Aug. '20. ROR Comm. is reviewing | WIP | MP updated
2 | Selectboard Policies | 1 | TM/SB | Working document. Awaiting Social Media policy. | WIP
2 | Sewer Rate Study | 2 | DPW/TM | An updated rate study will be presented to the sewer commissioners this fall. | WIP
2 | Short-term Rental Regulations | 2 | SB/TM/Planning Bd. | On hold for the time being. |  | SV Updated
2 | Sign Zoning (+Banners) | 2 | SPM/Builiding Dept. | Press release and article pending publication on website and FB | WIP | SV Updated
2 | Tax Classification (Kate) | 1
2 | Tree Committee | 1 |  | Added to 1-14-20 list. Request to discuss plantings/joint meeting with Tree Committee
2 | Website and URL for email addresses | LONG-RANGE | IT Director/Town Clerk |  |  | MP updated
2 | Zoning Enforcement | 1 | BLDG. DEPT | Active enforcement of zoning issues and signs. Proactive vs. Reactive approach | WIP
Completed Projects
3 | ADA Committee/Disability Related Issues | 1 | TM/BLDG | Commission formed. | Completed
3 | CodeRED Protocols | 1 | TM/EMD/FIRE/PD/BOH/DPW | Updated on 6-11-19 and effective on same. Outreach ongoing to large employers. | Completed | MP Updated
3 | Columbus Day/Indigenous Peoples' Day | LONG-RANGE | TM | Proclamation approved by SB | Completed
3 | Email Signatures for staff and SB | 1 | TM/IT Director | Standardized email signature for all gb.org accounts in place. Desktop only. | Completed
3 | Fire Station- Castle St. (lease status and surplus items) | 1 | ALL DEPTS/DPW | Building cleared on 11-20-20 and sold. Remediation work is beginning. | Completed
3 | Forensic Audit | 1 | TM/Finance Director/Treas | Substantially complete at this time. Information has been handed over to authorities. | Completed. | MP Updated
3 | Joint Meetings w/Planning Board | 1 | TM | Regular meetings held every other month. | WIP | MP updated
3 | Privacy Issues in Town Hall Offices | 1 | TM/DPW | Addressed by office move with Town Clerk and Assessor | Completed
3 | Senior Work-off Program (Re-boot) | 1 | TM | New forms, SWO member assigning tasks and working closely w/Seniors | Completed
3 | Standardize hours for Town Hall | 1 | TM | 8:30--4:00 M-F Full time staff on until 5:00 | Completed
3 | Town Counsel Policy (on use/access/etc.) | 1 | TM | SB Policies and Procedures approval on 7-22-19 | Completed
3 | Town Meeting(s) Schedule (2-night?) | 1 | TM/SB/Planning Bd | 2-Night ATM schedule approved by SB w/input from PB and Moderator | Completed
3 | Water Bottle Ban/Water in Public Buildings | 1 | TM | Water Stations installed and functional. Ban in full effect 11/1 Water stations in 3 locations | Completed
3 | Website Designate as Posting Board (Agendas) | 1 | Town Clerk | Approved by SB and Attorney General. Official posting location as of 1-1-20 | Completed
Key
Current High Priority Projects
| Items in-process noted in Yellow | SB= Selectboard | EDC= Econ. Dev. Committee
| Completed Items noted in Green | SPM= Special Projects Manager | TM= Town Manager | Last updated on 10/14/2020